## Sheet1
Final Project Completion Report
Project Name and Number: |  | 8518 South 960 East Well Pump Replacement, #4236
Description: The pumping equipment at the 8518 South 960 East well suffered mechanical failure due to a breach in the well casing. This construction contract included the installation of a stainless-steel well swage to repair the breach in the well casing, video inspection to verify proper placement of the well swage, and the installation of new pumping equipment.
District Project Manager: Kevin Rubow
Engineer: |  | CRS Engineering | Design Status: 100%
Original Engineering Contract Amount: |  |  | 13800
Final Engineering Contract Amount: |  |  | 13800
Contractor: |  | Nickerson Company | Construction Status: 100%
Original construction contract amount: |  |  | 124226
Total Change Order amount: |  |  | 0
Final construction contract amount: |  |  | 124226
Total change orders as a percentage of original contract: |  |  | 0%
Completion Schedule:
| Notice to Proceed: |  | 2021-12-14
| Final Completion: |  | 2022-09-14
Summary of Change Orders:
| Description |  | Amount
No change orders
| Total Change Order Amount: |  | 0
Final Project Completion Report
Staging equipment to install well swage
Fresh paint on pump discharge head and pump base
Pump to waste during well start-up
Adjusting hydraulic swage to patch the breach in the well
Staging the crane to install the new pump